## Phase_Task_Breakdown
Phase | Task Description | Subtasks | Total Hours
A. Project Kickoff & Setup | A.1 Dataset Connectivity – Connect Power BI Desktop to source files/tables (Calendar, Listings, Hosts, Reviews). | 1) Identify file formats (CSV/Excel/SQL) 2) Configure Power BI data sources (folder or database connection) 3) Verify refresh settings. | 10
B. Data Transformation & Cleaning | B.1 Power Query: Calendar Table Transformation – Clean “price” column, convert to numeric; Filter out invalid dates/rows. | Strip currency symbols/commas in “price”; Convert “available” to boolean; Handle missing “minimum_nights,” “maximum_nights”; Enforce proper date‐formats. | 10
B. Data Transformation & Cleaning | B.2 Power Query: Listings, Hosts & Reviews – Parse nested “amenities,” normalize host and review tables. | Split “amenities” into individual binary columns or a lookup table Trim/standardize text fields (“property_type,” “room_type,” etc.) Date‐format “host_since” and standardize “review_date.” | 10
C. Data Modeling & Relationships | C.1 Build Data Model – Create relationships among Calendar, Listings, Hosts, Reviews. | Identify primary/foreign keys (“listing_id,” “host_id”) Define relationships (Listings → Calendar, Hosts → Listings, Listings → Reviews) Enforce referential integrity in Power BI model view. | 15
C. Data Modeling & Relationships | C.2 Feature Aggregation (non‐ML) – Precompute aggregated review scores, host tenure, listing availability rates. | Use Power Query or DAX to compute: Average rating per listing Total number of reviews per listing Days active versus days rented Host age (current date − “host_since”).
D. DAX Calculations & Measures | D.1 Basic Measures – Create DAX measures: Total Active Days, Average Price, Availability Rate, Review Count, Host Age. | DAX for “ActiveDays” (COUNT rows where available = 1) “AvgPrice” per listing “AvailabilityRate” = ActiveDays / TotalDays “ReviewCount,” “HostAge,” “AvgRating,” etc. | 15
E. Advanced Analytics & Scenario Modeling | E.1 Parameterized What-If Scenarios (replacing ML) – Build “What-If” tables to let users adjust key drivers (occupancy %, minimum_nights, seasonal rate). | Create disconnected “What‐If” parameters (e.g., OccupancyRate, SeasonalMultiplier) Use DAX to calculate “ProjectedRevenue” and “ScenarioPrice” based on user‐selected sliders Add dynamic slicers that update key visual metrics. | 20
F. Visualization & UX Design | F.1 Design Core Report Pages – Build three key report pages: 1. Overview (Key metrics, filters) 2. Listing-Level Analysis (maps, price distribution) 3. Scenario Insights. | Page 1: KPI cards (Average Price, Avg AvailabilityRate, Total Listings, Avg OccupancyScenario); Page 2: Map (lat/long) colored by “AvgPrice”; histogram of actual “price”; Page 3: “What-If” scenario visuals (Projected Revs, scenario price distribution); Slicers: Date range, PropertyType, RoomType, “What-If” sliders. | 35
F. Visualization & UX Design | F.2 Enhance Interactivity & Tooltips – Drill-through, custom tooltips, bookmarks for storytelling. | Drill-through from a listing to detailed listing page; Custom tooltip showing host details, review metrics, occupancy scenario; Bookmarks for pre-scenario vs. post-scenario storytelling. | 10
G. Testing, QA & Optimization | G.1 Data Validation & DAX Testing – Verify that DAX measures match Power Query outputs; test “What-If” calculations. | Compare “AveragePrice” DAX vs. Power Query aggregation; Spot-check sample listings; Validate “ScenarioPrice” vs. manual calculations; Confirm data refresh doesn’t break measures. | 10
G. Testing, QA & Optimization | G.2 Performance Tuning – Optimize star schema, reduce cardinality, adjust visuals to minimize load times. | Identify high-cardinality columns; Optimize complex DAX (use VAR, minimize row-by-row iterations); Ensure visuals have page-level filters. | 5
H. Documentation & Deployment | H.1 User Guide & Technical Documentation – Write a one-page “How to Refresh & Use” guide; document data model, DAX formulas, and “What-If” steps. | User Guide: Steps to refresh data, how to use report, using “What-If” sliders; Technical Doc: Data Model diagram, DAX formulas list, Power Query M-code snippets, update “What-If” parameters instructions. | 10
H. Documentation & Deployment | H.2 Publish & Share – Publish the report to Power BI Service (workspace), configure row-level security if needed, share with stakeholders. | Upload .pbix to Power BI Service; Assign workspace permissions; Set up scheduled refresh.
I. Team Coordination & Meetings | I.1 Sprint Planning & Stand-ups – Hold a kickoff, daily stand-ups (15 min), mid-sprint review, and final demo. | Kickoff: 2h; Weekly stand-ups (1.5h); Mid-sprint review: 2h; Final demo: 2h; Retrospective: 2.5h. | 10

## Effort_Allocation
Learner | Assignments | Total Hours
L1 | A.1 Dataset Connectivity (10 h) B.1 Calendar Table Transformation (3 h) C.1 Data Model (5 h) D.1 Basic DAX Measures (5 h) I.1 Coordination (2 h) H.1 Documentation (5 h) | 30
L2 | B.2 Listings/Hosts/Reviews (7 h) C.1 Data Model (5 h) D.1 Basic DAX Measures (5 h) F.1 Visualizations (5 h) G.1 Data Validation (5 h) H.1 Documentation (3 h) I.1 Coordination (2 h) | 30
L3 | C.2 Feature Aggregation (5 h) D.1 DAX Measures (5 h) E.1 What-If Scenario Modeling (10 h) G.1 Data Validation (3 h) F.1 Visualizations (5 h) I.1 Coordination (2 h) | 30
L4 | E.1 What-If Scenario Modeling (10 h) F.1 Design Core Pages (15 h) G.2 Performance Tuning (3 h) I.1 Coordination (2 h) | 30
L5 | B.2 Listings/Hosts/Reviews (10 h) F.1 Design Core Pages (10 h) F.2 Interactivity & Tooltips (5 h) G.1 Data Validation (2 h) H.1 Documentation (2 h) I.1 Coordination (1 h) | 30

## Timeline
Week | Milestone/Deliverables
Week 1 | Kickoff (A.1 & I.1): L1 to configure all data sources, confirm connectivity Data Cleaning (B.1 & B.2): L1/L2/L5 to finish Calendar & Listings/Hosts/Reviews cleaning Initial Data Model (C.1): L1/L2/L3 validate relationships.
Week 2 | Feature Aggregation & DAX (C.2 & D.1): L1/L2/L3 finish aggregations L1/L2/L3 write all basic measures What-If Parameter Setup (E.1): L3/L4 build “What-If” tables and DAX UI Skeleton (F.1): L2/L3/L5 build first draft of Overview & Listing Analysis pages.
Week 3 | Visualization Refinement (F.1 & F.2): L2/L3/L4/L5 add interactivity/bookmarks/tooltips Testing & QA (G.1 & G.2): L2/L3/L4/L5 validate DAX, tune performance Documentation & Publish (H.1 & H.2): L1/L2/L5 finalize user guide + technical doc, publish to Power BI service Final Demo & Wrap-Up (I.1).

## Key_Deliverables
Deliverable | Details
Cleaned & Transformed Tables | Calendar_Clean (numeric price, Boolean available, valid dates) Listings_Clean (standardized text fields, split “amenities”) Hosts_Clean (valid “host_since,” calculated “HostAge”) Reviews_Clean (valid “review_date,” aggregated “ReviewCount”).
Data Model in Power BI | Star schema with relationships: Listings → Calendar (1:*) Hosts → Listings (1:*) Listings → Reviews (1:*).
DAX Measures & What-If Parameters | TotalActiveDays, AveragePrice, AvailabilityRate, ReviewCount, HostAge, AvgRating What-If tables: OccupancyRateParam, SeasonalMultiplierParam Measures: ProjectedRevenue and ScenarioPrice.
Power BI .pbix Report | Page 1: Overview (KPI cards: Avg Price Avg AvailabilityRate Total Listings ProjectedRevenue Slicers: Date range PropertyType RoomType OccupancyRate SeasonalMultiplier). Page 2: Listing Analysis (Map visual by “AveragePrice” Histogram of “price” distribution Table: Top 10 listings by ReviewCount or AvgRating). Page 3: Scenario Insights (Bar chart: “ScenarioPrice” vs. “AveragePrice” (top 20) Line chart: ProjectedRevenue vs. OccupancyRateParam Card: ProjectedRevenue Drill-through page for detailed listing view).
Documentation | User Guide PDF: Steps to refresh data how to navigate each page and use “What-If” sliders. Technical Document: Data Model diagram Full list of DAX formulas Power Query M-code snippets Instructions to update What-If parameter tables.
Published Power BI Service Workspace | .pbix uploaded to a shared workspace Row-level security configured (if required) Scheduled refresh set up Stakeholders have access.

## How_to_Use_Plan
Step | Details
Sprint Kickoff (Day 1) | L1 leads “Dataset Connectivity” Review roles/responsibilities Create shared folder (OneDrive/SharePoint) containing data files, project plan, Power BI .pbix template.
Daily Stand-ups | Each learner shares: what they completed yesterday what they plan today any blockers Use Scrum-board or Teams channel to track status.
Mid-Sprint Review (End of Week 2) | Demo: Cleaned data tables and relationships Basic DAX measures Initial What-If scenario page Collect feedback for rework.
Final Demo & Handover (End of Week 3) | Present all pages plus drill-through interaction and What-If functionality Walk through documentation Publish to Power BI Service and confirm scheduled refresh.
Retrospective | Identify what went well, what could be improved Document lessons learned in the technical doc.